## Sheet1
|  |  | 2018 |  |  |  | 2019 |  |  |  | 2020
Project | Status | Description | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
Project 0 | 100% | Data collection
Active shapes | 90% | Analysis | bar: 2018 Q1
| 75% | Writing | bar: 2018 Q1
| 0% | Submit, revisions | bar: 2018 Q1 to 2018 Q2
Project 1 | 0% | Data collection | bar: 2018 Q1 to 2018 Q3
Information metrics | 0% | Analysis | bar: 2018 Q1 to 2018 Q4
| 0% | Writing | bar: 2018 Q3 to 2018 Q4
| 0% | Submit, revisions | bar: 2018 Q4 to 2019 Q1
Project 2 | 0% | Develop code | bar: 2018 Q3 to 2018 Q4
Energy landscapes | 0% | Data collection | bar: 2018 Q4 to 2019 Q2
| 0% | Analysis | bar: 2019 Q1 to 2019 Q2
| 0% | Writing | bar: 2019 Q2 to 2019 Q3
| 0% | Submit, revisions | bar: 2019 Q2 to 2019 Q3
Project 3 | 0% | Data collection | bar: 2019 Q2 to 2019 Q3
Pluripotent materials | 0% | Analysis | bar: 2019 Q3 to 2019 Q4
| 0% | Writing | bar: 2019 Q3 to 2019 Q4
| 0% | Submit, revisions | bar: 2019 Q4 to 2020 Q1
Thesis | 0% | Data meeting | bar: 2020 Q1
| 0% | Defense | bar: 2020 Q2