## Sheet1
Key dates:
May 10: Prelim presentation
May 3: Written report due to the committee
Prelim preparation schedule:
| Item | Status | 2017-01-09 | 2017-01-13 | 2017-01-20 | 2017-01-27 | 2017-02-03 | 2017-02-10 | 2017-02-17 | 2017-02-24 | 2017-03-03 | 2017-03-10 | 2017-03-17 | 2017-03-24 | 2017-03-31 | 2017-04-07 | 2017-04-14 | 2017-04-21 | 2017-04-28 | 2017-05-05 | 2017-05-12
Meetings with Sharon
Setting expectations | bar: 2017-01-09
Review topic/research/questions | bar: 2017-03-03
Review draft | bar: 2017-04-07
Literature review
1 | Read "how to write a proposal" recommended by ChE department
Round 1: Identify key areas to research/read, schedule reading days | bar: 2017-01-09
Reading days
Paper writing
2 | Sketch up outline of what paper should look like and what information should be in there
Write down learnings so far
Presentation
Logistics
Committee Asks
Get advice from Sharon
Decide on/reach out to committee
Iterations
Iteration with Isaac | bar: 2017-03-17 to 2017-03-31
Checklist for a new project or paper
Literature review
Ask a question
Look up background papers on this question
Read and summarize key paper points
Go/no-go point: Keep, revise, or kill question
Construct a hypothesis
Design experiment to test this hypothesis
Paper
Mock up paper sections
Write up literature review
Write up methodology
Mock up what you expect results to be
Sketch out an put in figure placeholders
Write up discussion